## Worksheet
Measure | Items | Measure name | Indicative Implementation Date | Definitive Implementation Date | TA needs notified | Progress reported | Donor / Agency | TA Description | Tags
10.1 | 10.1.1 | Formalities | 30 June 2019 | 30 January 2023 | No | Yes | World Bank | Conduct an internal review of the formalities and documentation requirements for drawing up and implementing an improvement plan in conformity with the obligations set forth in the Article. ADDITIONAL INFORMATION: • Coordination by the Ministry of Foreign Trade and the National Council for Trade Facilitation with the support of the World Bank Group. | Legislative and regulatory framework, Diagnostic and Needs Assessment
10.2 | 10.2.2 | Acceptance of copies | 30 June 2019 | 30 January 2023 | No | Yes | World Bank | • Draw up a list of the documents required by the different governmental agencies for the exportation, importation, and transit of goods; • Design and implement a system for the exchange of information between governmental agencies. ADDITIONAL INFORMATION: • Coordination by the Ministry of Foreign Trade and the National Council for Trade Facilitation with the support of the World Bank Group. | Information and communication technologies (ICT), Diagnostic and Needs Assessment, Institutional procedures