## Worksheet
Measure | Items | Measure name | Indicative Implementation Date | Definitive Implementation Date | TA needs notified | Progress reported | Donor / Agency | TA Description | Tags
1.2 | 1.2 | Information available through internet | 31 December 2020 | 31 December 2022 | No | No |  | • Develop standards and requirements for information to be published • Develop a web portal on trade | Information and communication technologies (ICT), Legislative and regulatory framework
1.3 | 1.3 | Enquiry points | 31 December 2020 | 31 December 2020 | No | No |  | • Technical assistance and ICT support. • Develop regulations and standardized procedures | Information and communication technologies (ICT), Legislative and regulatory framework, Human resources and training
3 | 3 | Advance rulings | 31 December 2021 | 31 December 2021 | No | No |  | • Revise existing legislation, including in the context of the Customs Code of the Eurasian Economic Union • Conduct awareness campaigns • Train personnel | Legislative and regulatory framework, Human resources and training, Awareness-raising
5.3 | 5.3 | Test procedures | 31 December 2022 | 31 December 2023 | No | No |  | • Review existing legislation • Study from best practices • Conduct a feasibility study for creation of customs laboratory | Legislative and regulatory framework, Diagnostic and Needs Assessment
6.1 | 6.1 | General disciplines on fees and charges | 31 December 2019 | 31 December 2020 | No | No |  | • Review existing legislation | Legislative and regulatory framework
7.1 | 7.1 | Pre-arrival processing | 31 December 2020 | 31 December 2020 | No | No |  | • Conduct legal and institutional analysis of pre-arrival information and prior declaration • Implement technical module/interface on procedures of pre-arrival information and prior declaration • Train personnel • Conduct awareness campaigns | Diagnostic and Needs Assessment, Institutional procedures, Human resources and training, Awareness-raising
7.3 | 7.3 | Separation of release | 31 December 2020 | 31 December 2020 | No | No |  | • Analysis of international practice • Develop regulatory framework, including a methodology for risk management profiles | Legislative and regulatory framework
7.4 | 7.4 | Risk management | 22 February 2023 | 31 December 2023 | No | No |  | • Develop a concept and action plan on strategy of risks • Optimize and automate business processes for application of risk management system (RMS) • Capacity building of IT personnel • Analyse institutional framework of risk management system in customs authority • Develop terms of reference to modernize RMS module • Develop and implement RMS in authorized bodies for veterinary, phytosanitary and sanitary safety • Develop and implement interdepartmental system of risk management | Information and communication technologies (ICT), Legislative and regulatory framework, Institutional procedures, Human resources and training
7.5 | 7.5 | Post-clearance audit | 31 December 2023 | 31 December 2023 | No | No |  | • Optimize and automate business processes • Analyse and improve administrative procedures • Develop a software product/module • Train personnel | Information and communication technologies (ICT), Diagnostic and Needs Assessment, Institutional procedures, Human resources and training
7.6 | 7.6 | Average release times | 31 December 2021 | 31 December 2021 | No | No |  | • Train personnel • Conduct time release study at selected border checkpoints and publish it on websites of government agencies | Information and communication technologies (ICT), Human resources and training
7.7 | 7.7 | Authorized operators | 31 December 2021 | 31 December 2021 | No | No |  | • Train personnel • Adopt international standards ISO 17712:2013 Freight containers –Mechanical seals • Conduct awareness campaigns | Legislative and regulatory framework, Human resources and training, Awareness-raising
7.8 | 7.8 | Expedited shipments | 31 December 2020 | 31 December 2020 | No | No |  | • Simplify and automate the Express transportation procedure, including improving risk analysis and assessment • To conduct a pilot project on the basis of the Customs IS -harmonize the legal framework with improved business processes in the framework of the pilot project • Conduct trainings and seminars for Express carriers on new approaches to the procedure | Legislative and regulatory framework, Diagnostic and Needs Assessment, Human resources and training
8 | 8.1 | Border Agency Cooperation | 31 December 2020 | 31 December 2023 | No | No |  | • Review existing legislation • Analysis and optimize business processes • Train personnel | Legislative and regulatory framework, Institutional procedures, Human resources and training
8 | 8.2 | Border Agency Cooperation | 31 December 2022 | 31 December 2022 | No | No |  | • Analyse current situation • Develop recommendations on improvement of regional and international cooperation | Legislative and regulatory framework, Diagnostic and Needs Assessment
10.1 | 10.1.1 | Formalities | 31 December 2022 | 31 December 2022 | No | No |  | • Analysis of current requirements • Review and optimize operations and requirements • Harmonize data • Conduct awareness campaigns • Train personnel | Information and communication technologies (ICT), Diagnostic and Needs Assessment, Human resources and training, Awareness-raising
10.2 | 10.2 | Acceptance of copies | 31 December 2022 | 31 December 2022 | No | No |  | • Review existing legislation, including the adoption of law on electronic commerce • Implement electronic commercial documents • Integrate system of government agencies with a system of interdepartmental electronic interaction (electronic government) | Information and communication technologies (ICT), Legislative and regulatory framework, Institutional procedures
10.3 | 10.3.1, 10.3.2 | Use of international standards | 31 December 2022 | 31 December 2022 | No | No |  | • Assistance with developing a list of standards to be used • Analysis of application practices of international standards • Train personnel • Conduct awareness campaigns | Legislative and regulatory framework, Human resources and training, Awareness-raising
10.4 | 10.4 | Single window | 31 December 2022 | 31 December 2022 | No | No |  | • Implement electronic payments through a single window • Develop a monitoring mechanism | Information and communication technologies (ICT), Legislative and regulatory framework
10.9 | 10.9 | Temporary admission of goods and inward and outward processing | 31 December 2021 | 31 December 2021 | No | No |  | • Analysis of existing legislation and activity of free economic zones • Study international practice of free economic zones | Legislative and regulatory framework
11 | 11.5, 11.6, 11.7, 11.8, 11.9, 11.10, 11.11, 11.12, 11.13, 11.14, 11.16, 11.17 | Transit | 31 December 2020 | 31 December 2020 | No | No |  | • Analysis of transit procedures with possible amendment of existing legislation • Analysis of international laws and practice on guarantee • Develop and implement procedures for acceptance of guarantees in electronic format • Develop and implement a mechanism of insurance and guarantee , • Develop a regulation on national transit coordinator | Information and communication technologies (ICT), Legislative and regulatory framework
12 | 12.2, 12.3 | Customs cooperation | 31 December 2020 | 31 December 2023 | No | No |  | • Study international experience on exchange of information between customs agencies • Review existing legislation and if required, introduce changes into the legal framework • Examine the possibility of customs information system to verity declarations • Monitor the practice of protection and confidentiality, provision of information and postponement or refusal of a request | Information and communication technologies (ICT), Legislative and regulatory framework, Institutional procedures
12 | 12.4, 12.5, 12.6, 12.7 | Customs cooperation | 31 December 2020 | 31 December 2020 | No | No |  | • Study international experience on exchange of information between customs agencies • Review existing legislation and if required, introduce changes into the legal framework • Examine the possibility of customs information system to verity declarations • Monitor the practice of protection and confidentiality, provision of information and postponement or refusal of a request | Information and communication technologies (ICT), Legislative and regulatory framework, Institutional procedures
12 | 12.11, 12.12 | Customs cooperation | 31 December 2020 | 31 December 2022 | No | No |  | • Study international experience on exchange of information between customs agencies • Review existing legislation and if required, introduce changes into the legal framework • Examine the possibility of customs information system to verity declarations • Monitor the practice of protection and confidentiality, provision of information and postponement or refusal of a request , • Study the issues related to conclusion of bilateral or regional agreements | Information and communication technologies (ICT), Legislative and regulatory framework, Institutional procedures