## Worksheet
Measure | Items | Measure name | Indicative Implementation Date | Definitive Implementation Date | TA needs notified | Progress reported | Donor / Agency | TA Description | Tags
1.2 | 1.2 | Information available through internet | 31 December 2025 | 31 December 2025 | No | Yes |  | • Map existing IT infrastructure in all core agencies and identify the gaps for linking with the trade portal • Upgrade ICT infrastructure and software, and technical support to maintain and update the ICT platforms • Training of staff operating the system and awareness program for potential users of the trade portal | Information and communication technologies (ICT), Infrastructure and equipment, Diagnostic and Needs Assessment
4 | 4 | Procedures for appeal or review | 30 June 2025 | 31 December 2026 | No | Yes |  | • Design the structure of the new forum for appeals and review along with the new workflow processes • Training and capacity building of the Customs staff | Legislative and regulatory framework, Human resources and training
5.1 | 5.1 | Notifications for enhanced controls or inspections | 31 December 2025 | 31 December 2030 | No | Yes |  | • Review all relevant laws and rules to incorporate provisions for immediate termination of enhanced controls when risk is neutralized • IT infrastructure for establishing and running automated controls system • Training of staff of core agencies for implementing risk-based system and for implementation of enhanced controls • Support to design of the monitoring mechanism • Cross-country experience sharing and its replication in Nepal's context | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Human resources and training
5.3 | 5.3 | Test procedures | 31 December 2027 | 31 December 2030 | No | Yes |  | • Conduct gap analysis in the laws and the IT infrastructure in each agency • Develop risk-based system with the issuance of notices and reports for test procedures • Provide technical training and equipment for next generation genome sequencing (NGS)/high sequencing and genomic analysis of plant viruses for verification of compliance in trade • Strengthen laboratories and prepare a consolidated database for the laboratories • Review the scope of laboratories and cross-country experience sharing and its replication in Nepal's context | Information and communication technologies (ICT), Legislative and regulatory framework, Diagnostic and Needs Assessment, Institutional procedures
7.4 | 7.4 | Risk management | 31 December 2027 | 31 July 2028 | No | Yes | ADB | • Draft the relevant provisions in the legal documents/policies/SOPs for risk-based profiling, selection, feedback loops • Automate implementation of risk management system and link all implementing agencies for risk management implementation • Establish integrated risk management system • Develop diagnostic protocols for pests • Strengthen e-Phyto system • Support in pest risk analysis • Support in development, testing and implementation of online sapling tracking system for post entry quarantine and internal quarantine management • Support in strengthening national quarantine systems in the areas identified in the third-party assessment • Staff training and capacity-building in risk assessment, risk-based inspection, pest risk analysis and risk-based | Information and communication technologies (ICT), Legislative and regulatory framework, Diagnostic and Needs Assessment, Human resources and training
7.7 | 7.7 | Authorized operators | 31 December 2027 | 31 December 2027 | No | Yes |  | • Amend the legal provisions in line with the requirements of the TFA • Set up processes for online application for authorized operator and devise the selection criteria • Cross-country experience sharing and its replication in Nepal's context • Staff training and capacity building | Information and communication technologies (ICT), Legislative and regulatory framework, Human resources and training
7.8 | 7.8 | Expedited shipments | 31 December 2027 | 31 December 2028 | No | Yes |  | • Review the legal provision for expedited shipments for qualifying goods • ICT infrastructure and software to automate the processes for online processing of requests for expedited shipments | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment
8 | 8 | Border Agency Cooperation | 31 December 2027 | 31 December 2030 | No | Yes |  | • Establish functional mechanisms (including MoUs) between/among agencies • Prepare a master plan for common facilities and develop SOPs for border agency cooperation • Designing mechanisms for sharing of data and information • Capacity building and staff training on border agency cooperation and international best practices • Cross-country experience sharing and its replication in Nepal's context • ICT support to engineer new business processes | Information and communication technologies (ICT), Legislative and regulatory framework, Human resources and training
9 | 9 | Movement of goods | 31 December 2027 | 31 December 2031 | No | Yes |  | • Introduce automated tracking of consignments within Customs authorities from end to end • Staff training and capacity building for the usage of the new systems and processes | Information and communication technologies (ICT), Human resources and training
10.1 | 10.1.1 | Formalities | 31 December 2025 | 31 December 2026 | No | Yes |  | • Review document and formalities across all agencies and suggest simplification, standardization, and harmonization • Develop testing and accreditation facilities • Conduct awareness training programs for producers, traders and exporters about certification processes • Organize awareness programs for SMEs, cottage industries and handicrafts producers for quality enhancement • Develop a system for periodic review • Staff training and capacity building | Information and communication technologies (ICT), Legislative and regulatory framework, Institutional procedures, Human resources and training, Awareness-raising
10.3 | 10.3.1, 10.3.2 | Use of international standards | 31 December 2029 | 31 December 2030 | No | Yes | WCO | • Conduct periodic review of international standards and lessons learned for implementation • Conduct regular gap analysis, review of the processes, forms and documents required to align with international standards • Revise systems and processes based on the lessons learned • Training and capacity building of staff on international standards requirements and use of new business processes as well as IT enabled systems and processes • Support to review legal provisions on customs law and requisite subsidiary legislation in place for consistent implementation across multiple agencies | Information and communication technologies (ICT), Legislative and regulatory framework, Human resources and training
10.4 | 10.4 | Single window | 31 December 2032 | 31 December 2026 | No | Yes | World Bank | • Strengthen e-Phyto system • Staff training and capacity building • Awareness raising and capacity building of private sectors on use and benefits of single window | Legislative and regulatory framework, Human resources and training, Awareness-raising
12 | 12 | Customs cooperation | 31 December 2029 | 31 December 2032 | No | Yes |  | • Cross country experience sharing and compliance regime • Training and capacity building | Legislative and regulatory framework, Human resources and training