## Worksheet
Measure | Items | Measure name | Indicative Implementation Date | Definitive Implementation Date | TA needs notified | Progress reported | Donor / Agency | TA Description | Tags
1.1 | 1.1.1 | Publication | 22 February 2025 | 30 June 2030 | No | No |  | There is a need for support: • To designate and empower an institution to periodically collect, analyse, publish and make trade information publicly available. | Information and communication technologies (ICT), Institutional procedures
1.2 | 1.2 | Information available through internet | 22 February 2026 | 30 June 2030 | No | Yes | ITC, UNCTAD | There is a need for support to: • Ensure sustainability of Trade Information Module/Portal; • Continuously collect information and update the portal; • Build capacity to Portal Management Team; and • Create awareness on the use of Portal. | Information and communication technologies (ICT), Human resources and training, Awareness-raising
1.3 | 1.3 | Enquiry points | 22 February 2025 | 30 June 2030 | No | No |  | There is a need for support to: • Establish and/or strengthen the existing enquiry points; and • Train and build capacity for the staff at the enquiry points to reply enquiries. | Information and communication technologies (ICT), Human resources and training
2.2 | 2.2 | Consultations | 22 February 2025 | 30 June 2030 | No | No |  | There is need to: • Strengthen Regular Joint Border Committee Meetings (JBCs) | Human resources and training
5.3 | 5.3 | Test procedures | 22 February 2026 | 30 June 2030 | No | No |  | There is a need for a support to: • Review or to develop national regulations on the second testing; • Establish second test laboratories to be full capacitated in terms of testing facilities, training of staff and accreditation process; • Establish customs laboratories for customs operations; and • Strengthen and accredit the existing labs in testing Institutions (TBS, GCLA, Plant Health Labs, TMDA, ZFDA, ZBS, CGCLA-Zanzibar) to build confidence to importers and exporters. | Legislative and regulatory framework, Infrastructure and equipment, Human resources and training
6.1 | 6.1 | General disciplines on fees and charges | 22 February 2030 | 30 June 2030 | No | No |  | There is a need for support to: • Conduct studies fees and charges including their numbers and diversity; • Establish mechanism for periodic review of fees and charges; and • Timely publish the information on fees and charges. | Information and communication technologies (ICT), Legislative and regulatory framework, Diagnostic and Needs Assessment
6.2 | 6.2 | Specific disciplines on fees and charges | 22 February 2030 | 30 June 2030 | No | No |  | There is a need for support to: • Conduct studies for customs processing fees and charges and advice accordingly | Diagnostic and Needs Assessment
7.4 | 7.4 | Risk management | 22 February 2025 | 30 June 2028 | No | No |  | There is a need for support to: • Strengthen the system on sampling procedures and sampling management; • Establish interconnectivity between the scanner and customs system (TANCIS); • Secure scanners and other modern technology to equip those borders with no such facilities; and • Build capacity to the TRA staff and Border Agencies. | Information and communication technologies (ICT), Infrastructure and equipment, Human resources and training
7.7 | 7.7 | Authorized operators | 22 February 2025 | 30 June 2030 | No | Yes | TMA, COMESA | There is a need for a support to: • Create a country wide sensitization and awareness to exporters, importers, Clearing and Forwarding Agencies (CFAs), transporters on the Authorized Economic Operators (AEO) program and criteria there-off; • Select basing on specified criteria, operators who qualify for AEOs and continuously build their capacity; and • Develop a national framework or mechanism for coordinating and cooperating between customs and border agencies in relation to AEOs. | Institutional procedures, Human resources and training, Awareness-raising
7.9 | 7.9 | Perishable goods | 22 February 2025 | 30 June 2035 | No | No |  | There is a need for support to: • Develop infrastructure (e.g. cold room, safety cages for animals) for fast-tracking clearance and handling of perishable goods at the main entry/exit points | Infrastructure and equipment
8 | 8 | Border Agency Cooperation | 22 February 2025 | 30 June 2030 | No | No |  | There is a need for support to: • Establish shared facilities for the remaining border posts (Horohoro, Mtambaswala, Ileje, Kabwe, Kasesya, Kasumulu and Lunga lunga) as well as harmonizing procedures and formalities; • Create sustainability of existing OSBPs; strengthening the instructional Framework, Capacity building, maintenance and management of OSBPs Standards; • Support the soft infrastructure at Horohoro-Lungangunga, Sirari-Isebania; and Establish and operationalize one Stop Border Post Control with Mozambique (MTAMBASWALA-NENGOMANO) and with Malawi (‘Kasumulo-Songwe); Manyovu-Mugina; OSBP /Tanzania/Burundi and others with potential growth of trade. | Legislative and regulatory framework, Infrastructure and equipment, Institutional procedures
10.1 | 10.1.1 | Formalities | 22 February 2025 | 30 June 2030 | No | No |  | Need financial support to: • Conduct studies and consultative meetings on formalities and documentation requirements; and • Perform periodic review/analysis of formalities and documentation requirements with a view to simplification and reducing their numbers. | Legislative and regulatory framework, Diagnostic and Needs Assessment
10.4 | 10.4 | Single window | 22 February 2025 | 30 December 2028 | No | Yes | AfDB | There is a need for a support to: • Acquire and put in place adequate facilities for single window; • Upgrading ICT system for Other Government Departments to enable system integration with single window; • Create awareness program, Change Management and training to users; and • Develop mechanism for information sharing among border agencies. | Information and communication technologies (ICT), Infrastructure and equipment, Institutional procedures, Human resources and training, Awareness-raising
10.7 | 10.7 | Common border procedures | 22 February 2025 | 30 June 2030 | No | No |  | There is a need for support to: • Undertake study with a view to Harmonizing documentation requirements and procedures; and • Build capacity and upgrading infrastructure at border posts. | Infrastructure and equipment, Diagnostic and Needs Assessment
11 | 11 | Transit | 22 February 2024 | 30 June 2035 | No | No |  | There is a need for support to: • The expansion of the port (lanes, berth, off-loading and loading cranes for transit goods; • Improve infrastructure along the transit routes; and • Strengthen cargo tracking system and banal system to secure transit. | Information and communication technologies (ICT), Infrastructure and equipment
12 | 12 | Customs cooperation | 22 February 2025 | 30 June 2030 | No | No |  | There is a need for support to: • Undertake awareness creation and capacity building for Customs Officials on issues of cooperation with other customs authorities. | Human resources and training, Awareness-raising